## VesselVisitDetails_20260902_091
Displaying 10 item(s) at 2026-09-02
Visit | Vessel Name | Line | Vessel Class | I/B Vyg | O/B Vyg | Phase | Est. Time of Berth | ETD | ETA | ATA | ATD | ATB | Service | Vessel Loa M | BEAM M | Berthside | Bollard Fore | Bollard Fore offset | Bollard Aft | Bollard Aft offset | Draft Forward | Draft Aft | Est Disch | Previous Port | Next Port | EST Loading | Additional Moves | Total Moves | vessel berth
TSSNTSGP2606W | TS SINGAPORE | TSL | TSSN | TSGP2606W | TSGP2606W | Inbound | 26-Sep-02 0800 | 26-Sep-04 1900 | 30-08-2026 1900 |  |  |  | ADHOC | 260 | 32 | Starboardside | 1R19 | 6 | 1R2 | 1 |  |  |  |  | JIB |  |  |  | R1
TROD25618 | TRANSMAR ODYSSEY | AET | TROD | 25618 | 25618 | Inbound | 26-Sep-02 1800 | 26-Sep-03 1900 | 02-09-2026 1700 |  |  |  | RES | 161 | 25 | Starboardside | 4B15 | -5 | 4B4 | -1 |  |  | 520 |  | EGADA | 400 |  | 920 | B4
TSMNKRTM2634E | KR TASMAN | CUL | TSMN | KRTM2634E | KRTM2634E | Inbound | 26-Sep-03 0100 | 26-Sep-05 0500 | 2026-09-02 2300 |  |  |  | REX-2 | 192 | 28 | Starboardside | 6B47 | -9 | 6B36 | 4 |  |  | 851 | PKG | SOK | 900 |  | 1751 | B6
DANIIRS03W26 | DANIEL A | ARL | DANI | IRS03W26 | IRS03W26 | Inbound | 26-Sep-03 0200 | 26-Sep-04 0500 | 03-09-2026 0001 |  |  |  | TRI-NB | 155 | 24.5 | Portside | 4R12 | 4 | 4R23 | -6 |  |  | 500 | AQJ | NSA | 657 |  | 1157 | R4
DKUT003 | DEDE KORKUT | ZSL | DKUT | 003 | 003 | Inbound | 26-Sep-03 0600 | 26-Sep-04 1100 | 26-08-2026 1900 |  |  |  | ADHOC | 210 | 31 | Starboardside | 5B33 | 0 | 5B19 | 0 |  |  | 1038 |  | JIB |  |  | 1038 | B5
SIMOIS636E | MSC SIMONA | MSC | SIMO | IS634R | IS634R | Inbound | 26-Sep-03 1600 | 26-Sep-05 1900 | 2026-09-03 1400 |  |  |  | ADHOC | 366 | 51 | Starboardside | 3R65 | 0 | 2R37 | -2 | 16.6 | 16.6 | 2136 | AKI | JIB | 2898 |  | 5034 | R3
TENVTNVN2632E | TEN VENUS | CUL | TENV | TNVN2632E | TNVN2632E | Inbound | 26-Sep-04 0100 | 26-Sep-07 0800 | 2026-09-03 2300 |  |  |  | REX-2 | 175 | 27.5 | Starboardside | 4B15 | 3 | 4B3 | 7 |  |  | 970 | PKG | SOK | 1000 |  | 1970 | B4
CCPE0MXOYE1MA | CMA CGM PELLEAS | CMA | CCPE | 0MXOYE1MA | 0MXOYE1MA | Inbound | 26-Sep-04 0900 | 26-Sep-05 1400 | 04-09-2026 0700 |  |  |  | MEDEX-E | 350 | 42 | Portside | 4R6 | -4 | 4R29 | 2 |  |  | 1129 |  | PIR | 1200 |  | 2329 | R4
KHDZKDHZ2636W | KAI DA HONG ZHOU | CUL | KHDZ | KDHZ2636W | KDHZ2636W | Inbound | 26-Sep-04 1300 | 26-Sep-06 0300 | 04-09-2026 1100 |  |  |  | ADHOC | 149 | 24 | Starboardside | 5B31 | -1 | 5B21 | 1 |  |  | 589 |  | JIB | 620 |  | 1209 | B5
CMAPPHXSSSE19 | CMA CGM MAPUTO | CMA | CMAP | PHXSSSE19 | PHXSSSE19 | Inbound | 26-Sep-04 2100 | 26-Sep-06 0700 | 04-09-2026 1900 |  |  |  | MED5 | 175 | 27 | Starboardside | 1R17 | -7 | 1R5 | -2 |  |  | 394 |  | SHK | 1375 |  | 1769 | R1
APOLRX2030E19 | CMA CGM APOLLON | CMA | APOL | RX2030E19 | RX2030E19 | Working | 26-Sep-02 1800 | 26-Sep-03 2000 | 28-08-2026 2300 | 26-Aug-31 0350 |  | 2026-08-31 0320 | RES2EB | 366 |  | Starboardside | 3R65 | 0 | 2R37 | -2 | 14.2 | 14.2 | 2888 | JIB | SOK | 1586 |  | 4474 | R3
CHMNCUHM2635W | CUL HUMEN | CUL | CHMN | CUHM2635W | CUHM2635W | Working | 26-Sep-01 1000 | 26-Sep-03 0300 | 2026-09-01 0300 | 26-Sep-01 1032 |  | 01-09-2026 1000 | REX-2 | 184 |  | Portside | 4R11 | 5 | 4R24 | -7 | 9.1 | 9.5 | 746 | PKG | SOK | 642 |  | 1388 | R4
LDRB2602S | LDR BEDEL | OVP | LDRB | 2602N | 2602N | Working | 26-Sep-01 1600 | 26-Sep-03 0400 | 01-09-2026 1100 | 26-Sep-01 1715 |  | 01-09-2026 1700 | ADHOC | 113 |  | Starboardside | 5B30 | -3 | 5B22 | 3 | 6.6 | 7.7 | 175 |  | JIB | 63 |  | 238 | B5